## COE-1827
AutomationName | Page | RowIndex | URL | FullUrl | Status
IL Engagement flow 20 | 1 | 2 | /uipath/automation-profile/il-engagement-flow-20 | https://connect-enterprise.uipath.com/uipath/automation-profile/il-engagement-flow-20 | Ongoing

## COE-1827_SubTask
SubTask | Status | Key | Url
PDD | DONE | COE-1828 | /browse/COE-1828
Development | DONE | COE-1829 | /browse/COE-1829
DSD | DONE | COE-1830 | /browse/COE-1830
UAT | DONE | COE-1831 | /browse/COE-1831
Deploy to production | DONE | COE-1841 | /browse/COE-1841

## COE-1688
AutomationName | Page | RowIndex | URL | FullUrl | Status
Banking Platform to Kyriba Streamline | 1 | 9 | /uipath/automation-profile/banking-platform-to-kyriba-streamline | https://connect-enterprise.uipath.com/uipath/automation-profile/banking-platform-to-kyriba-streamline | Ongoing

## COE-1688_SubTask
SubTask | Status | Key | Url
Banking Platform to Kyriba Streamline - PDD | DONE | COE-1689 | /browse/COE-1689
Banking Platform to Kyriba Streamline - Development | DONE | COE-1690 | /browse/COE-1690
Banking Platform to Kyriba Streamline - DSD | DONE | COE-1691 | /browse/COE-1691
Banking Platform to Kyriba Streamline - UAT | DONE | COE-1692 | /browse/COE-1692
Banking Platform to Kyriba Streamline - Deployment | DONE | COE-1887 | /browse/COE-1887

## COE-1827_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
IL Engagement flow 20 | 1 | 1 | /uipath/automation-profile/il-engagement-flow-20 | https://connect-enterprise.uipath.com/uipath/automation-profile/il-engagement-flow-20 | Ongoing

## COE-1688_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Banking Platform to Kyriba Streamline | 1 | 1 | /uipath/automation-profile/banking-platform-to-kyriba-streamline | https://connect-enterprise.uipath.com/uipath/automation-profile/banking-platform-to-kyriba-streamline | Ongoing

## COE-1914_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Follow SF Tickets for my customers | 1 | 1 | /uipath/automation-profile/follow-sf-tickets-for-my-customers | https://connect-enterprise.uipath.com/uipath/automation-profile/follow-sf-tickets-for-my-customers | On Track

## COE-1914_SubTask
SubTask | Status | Key | Url
PDD | In Progress (On Track) | COE-1923 | /browse/COE-1923
Development | To Do | COE-1924 | /browse/COE-1924
Follow SF Tickets for my customers - Code Review | In Progress (On Track) | COE-2118 | /browse/COE-2118
DSD | To Do | COE-1925 | /browse/COE-1925
UAT | To Do | COE-1926 | /browse/COE-1926
Deploy to production | To Do | COE-1927 | /browse/COE-1927

## COE-1898_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Hiring Manager Bot | 1 | 1 | /uipath/automation-profile/hiring-manager-bot | https://connect-enterprise.uipath.com/uipath/automation-profile/hiring-manager-bot | On Track

## COE-1898_SubTask
SubTask | Status | Key | Url
PDD - Hiring Manager Bot | Done | COE-1899 | /browse/COE-1899
Hiring Manager Bot - Development (Dispatcher) | In Progress (On Track) | COE-1900 | /browse/COE-1900
Hiring Manager Bot - Code Review (Dispatcher) | Done | COE-2117 | /browse/COE-2117
Hiring Manager Bot - Development (Performer) | To Do | COE-2113 | /browse/COE-2113
Hiring Manager Bot - DSD | To Do | COE-1901 | /browse/COE-1901
UAT (Dispatcher) | To Do | COE-1902 | /browse/COE-1902
UAT (Performer) | To Do | COE-2114 | /browse/COE-2114
Hiring Manager Bot - Go Live (Dispatcher) | To Do | COE-2115 | /browse/COE-2115
Hiring Manager Bot - Go Live (Performer) | To Do | COE-2116 | /browse/COE-2116

## COE-1781_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Sync Enterprise Connect with JIRA | 1 | 1 | /uipath/automation-profile/sync-enterprise-connect-with-jira | https://connect-enterprise.uipath.com/uipath/automation-profile/sync-enterprise-connect-with-jira | On Track

## COE-1781_SubTask
SubTask | Status | Key | Url
PDD | Done | COE-1782 | /browse/COE-1782
Development CE to JIRA sync | In Progress (On Track) | COE-1783 | /browse/COE-1783
Development JIRA to CE sync | In Progress (On Track) | COE-1915 | /browse/COE-1915
DSD - CE to JIRA sync | In Progress (On Track) | COE-1784 | /browse/COE-1784
DSD - JIRA to CE sync | In Progress (On Track) | COE-1916 | /browse/COE-1916
UAT | To Do | COE-1785 | /browse/COE-1785
Deployment to production | To Do | COE-1917 | /browse/COE-1917

## COE-1756_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Opportunity Qualifier | 1 | 1 | /uipath/automation-profile/opportunity-qualifier | https://connect-enterprise.uipath.com/uipath/automation-profile/opportunity-qualifier | On Track

## COE-1756_SubTask
SubTask | Status | Key | Url
Opportunity Qualifier - PDD | Done | COE-1757 | /browse/COE-1757
Opportunity Qualifier - Development | Done | COE-1758 | /browse/COE-1758
Opportunity Qualifier - DSD | To Do | COE-1759 | /browse/COE-1759
Opportunity Qualifier - UAT | To Do | COE-1760 | /browse/COE-1760

## COE-1670_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Carta equity tax reporting | 1 | 1 | /uipath/automation-profile/carta-equity-tax-reporting | https://connect-enterprise.uipath.com/uipath/automation-profile/carta-equity-tax-reporting | On Track

## COE-1670_SubTask
SubTask | Status | Key | Url
Carta equity tax reporting - PDD | Done | COE-1671 | /browse/COE-1671
Carta equity tax reporting - Development - file processing and upload to sharepoint | In Progress (Off Track) | COE-1672 | /browse/COE-1672
Carta equity tax reporting - Development - Download report from Carta | In Progress (Off Track) | COE-1741 | /browse/COE-1741
Carta equity tax reporting - DSD | To Do | COE-1673 | /browse/COE-1673
Carta equity tax reporting - UAT | To Do | COE-1674 | /browse/COE-1674
Execution Planning | To Do | COE-1742 | /browse/COE-1742
Launch Communication | To Do | COE-1743 | /browse/COE-1743
BOT On-boarding (deployment) | To Do | COE-1744 | /browse/COE-1744

## COE-1432_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Reject candidates in Lever based on Territory | 1 | 1 | /uipath/automation-profile/reject-candidates-in-lever-based-on-territory | https://connect-enterprise.uipath.com/uipath/automation-profile/reject-candidates-in-lever-based-on-territory | On Track

## COE-1432_SubTask
SubTask | Status | Key | Url
PDD | Done | COE-1433 | /browse/COE-1433
Development | In Progress (On Track) | COE-1435 | /browse/COE-1435
DSD | In Progress (On Track) | COE-1434 | /browse/COE-1434
UAT | To Do | COE-1436 | /browse/COE-1436

## COE-1301_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Automatic upload of invoices in different portals | 1 | 1 | /uipath/automation-profile/automatic-upload-of-invoices-in-different-portals | https://connect-enterprise.uipath.com/uipath/automation-profile/automatic-upload-of-invoices-in-different-portals | On Track

## COE-1301_SubTask
SubTask | Status | Key | Url
PDD | Done | COE-1302 | /browse/COE-1302
Development | Done | COE-1303 | /browse/COE-1303
DSD | Done | COE-1304 | /browse/COE-1304
UAT | In Progress (On Track) | COE-1305 | /browse/COE-1305
CR Automatic upload of invoices in different portals | To Do | COE-1863 | /browse/COE-1863

## COE-534_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Automated reminders for candidates to submit test | 1 | 1 | /uipath/automation-profile/automated-reminders-for-candidates-to-submit-test | https://connect-enterprise.uipath.com/uipath/automation-profile/automated-reminders-for-candidates-to-submit-test | On Track

## COE-534_SubTask
SubTask | Status | Key | Url
PDD | Done | COE-747 | /browse/COE-747
Development | Done | COE-749 | /browse/COE-749
DSD | Done | COE-748 | /browse/COE-748
UAT | In Progress (On Track) | COE-750 | /browse/COE-750

## COE-470_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Bulk Payment Posting for Credit Cards | 1 | 1 | /uipath/automation-profile/bulk-payment-posting-for-credit-cards | https://connect-enterprise.uipath.com/uipath/automation-profile/bulk-payment-posting-for-credit-cards | Completed

## COE-470_SubTask
SubTask | Status | Key | Url
PDD | Done | COE-471 | /browse/COE-471
NetSuite Create Journal component | Done | COE-2035 | /browse/COE-2035
Development | In Progress (On Track) | COE-472 | /browse/COE-472
DSD | To Do | COE-473 | /browse/COE-473
UAT | To Do | COE-474 | /browse/COE-474
BOT On-boarding (deployment) | To Do | COE-1755 | /browse/COE-1755
CR Bulk Payment Posting for Credit Cards | Done | COE-1947 | /browse/COE-1947

## COE-1470_Connect
AutomationName | Page | RowIndex | URL | FullUrl | Status
Global Marketing Events Robot | 1 | 1 | /uipath/automation-profile/amer-marketing-events-robot | https://connect-enterprise.uipath.com/uipath/automation-profile/amer-marketing-events-robot | In Progress

## COE-1470_SubTask
SubTask | Status | Key | Url
AMER Marketing Events Robot - PDD | Done | COE-1471 | /browse/COE-1471
PDD update | Done | COE-2060 | /browse/COE-2060
Global Marketing Events Robot - Development 1 | Done | COE-1472 | /browse/COE-1472
Global Marketing Events Robot - Development 2 | In Progress (On Track) | COE-2061 | /browse/COE-2061
Global Marketing Events Robot - DSD | In Progress (On Track) | COE-1473 | /browse/COE-1473
Global Marketing Events Robot - UAT | In Progress (On Track) | COE-1474 | /browse/COE-1474
Global Marketing Events Robot 1 - CR Akkroo to Integrate Events Update | In Progress (On Track) | COE-2171 | /browse/COE-2171
Global Marketing Events Robot 1 - Code Review | To Do | COE-2181 | /browse/COE-2181